Engaging the architect and design approval process

- Introduction

The purpose of the design development and approval process is to ensure that the facility is designed to the acceptable and mandated standards, constructed within an acceptable budget and time frame, satisfying the functional, social, and aesthetic expectations of the client (the entity wanting to build the hospital) and patients. The role of the architect is paramount in this design process. Thus, there needs to be mutual clarity both on the design process and on the roles of the client and the architect. While the details are likely to vary from place to place based on the established practices, the following is proposed as a comprehensive template.  In reality, the actual responsibility for specific items may shift between the client and the architect.

- The approval process - A five-stage process integrated within the general design process

The approval process consists of the following five stages as illustrated.  This design and approval process if done well should ensure the construction drawing; documentation and execution stages can proceed without the need for any intervention from the client team.  Each stage is marked with

This section will focus on stages I, II and IV in detail since the other two stages are straightforward in terms of the details.

- Preliminary design submission

- Purpose

To allow the client to identify major design anomalies or misunderstandings of the intent or any statutory/regulatory constraints that may affect the project schedule/outcome before the detailed development of the design. The first submission of the documentation is expected at the schematic design level. Approval in writing to proceed will be a prerequisite for stage II.

- Process

Stage I submission will follow:

- Detailed study of guidelines and the statutory requirements by the architect, a visit to a similar facility, and a request for clarifications if any. The client team will clarify any aspects raised by the architect that may influence the preliminary design. This shall be accomplished within stipulated days of the architect being given these guidelines.

- The drawings and documents in compliance described on the Deliverables for schematic submission shall be submitted in printed and digital form to the client within the prescribed time limit

- The client shall evaluate the submission and in writing give comments/suggestions for a revised submission or for proceeding to stage II. If a revised submission is requested, the time for revision shall be agreed upon mutually.

The approved documents are then lodged in both hard copy and soft copy (pdf) for documentation purposes by the client.

- Considerations

Only two rounds of schematic submissions are recommended to ensure speedy progress.  The client and the architect shall work closely to ensure the Preliminary Design Stage is completed to the satisfaction of the client within the two submissions.

- Deliverables

The following drawings and documents shall be submitted in hard and soft copies;

- Site analysis report, highlighting applicable zoning and building by-laws, levelling and drainage proposals, and environmental considerations

- Preliminary master plan showing placement and orientation of blocks, entries and exits, and internal circulation.

- Schematic floor plans indicating the arrangement of rooms and sections indicating heights. The basement (if applicable) and entry levels regarding the site and roads shall be shown.

- Any deviation/ noncompliance from the guidelines shall be presented in the form of a deviation document with reasons for the deviation/noncompliance.

- Statement of areas, coverage, FAR (floor area ratio)/FSI (floor space index)

- Preliminary design report on explaining the architectural design approach with reference images for understanding form and aesthetics.

- Any additional drawings/documents which the architect desires.

- Block estimate

- Concept design submissions

- Purpose

Concept Design Submission stage II is to enable the client to visualize the project in terms of floor areas, and the number of floors and to gain an understanding of the engineering services and sustainability measures being incorporated.  This should enable the client to know how the design meets their vision and requirements. The clinical/management team could begin (a) high-level preparation for equipping and staffing the facility and (b) budgeting for initial recurring expenditures. The client will approve the plans and areas, proposed engineering systems, finishes, and budgetary estimates.

Final design submission would enable the client to sign off the design process and allow progression to statutory approvals and construction.

- Process

Stage II will commence on written approval to proceed, after the completion of stage I, by the client. The architect shall incorporate any inputs/comments while developing the design. The structural and services engineering inputs will be considered and incorporated.

The Master Plan and floor plans with the location of doors and windows and internal dimensions of the rooms will be submitted to show compliance with these guidelines.

Any suggestions/comments/inputs will be considered by the architect.  Concept design with layouts of furniture will be submitted for the client’s approval. Proposals for all engineering systems, finishes, and budgetary estimates submitted will be approved with suggestions/comments by the client to proceed to the final phase of design.

The final concept design will incorporate any suggestions/comments/input on the stage II submission and will comprise a Master plan with the landscape, floor plans with furniture layouts, envelope design, and interiors. All guidelines in this document, other than expressly accepted deviations would have complied with the design. All statutory requirements are met and provisions for all engineering services are incorporated in the drawings. In essence, every design decision that influences the outcome of the project and requires the consent of the client would be obtained and recorded in drawings and documents and submitted for the approval of the client.

- Considerations

If desired, the client may request one revised submission of the master plan and floor plans in stage II to enable finalization and acceptance of the master plan and the floor plans and sign-off on areas.

The architect shall incorporate changes in the aesthetics, form of the buildings, and selection of materials as desired by the client. The final designs shall enable the client to sign off inputs on all aspects of the design.

- Deliverables in stage II

The following drawings and documents shall be submitted in hard and soft copies.

- Final master plan with roads, footpaths and drains, and levels.

- Floor plans with doors and windows and layout of furniture and room inner dimensions and room areas.

- Architectural design report.

- Design basis and approach reports for structural, electrical, plumbing, HVAC, fire alarm, firefighting, building management systems, and landscape designs from consultants.

- Schedule floor wall and ceiling finishes.

- Statement of areas

- Landscape drawing showing hard and soft treatments

- Drainage plan

- Sections and elevations sufficient to explain the design

- Specifications in brief for all materials and systems proposed in the design

- Preliminary designs for structural, electrical, plumbing, HVAC, fire alarm, and firefighting and building management systems

- Budgetary estimate for the entire project including all engineering services

- Artist’s renderings of the project, both interior and exterior sufficient for the client to appreciate and approve the design

- Scale model of the project (optional)

- Statutory approval submission

- Purpose

To obtain a building permit

- Process

The architect will identify all the statutory approvals required to commence the construction of the project. The client will be made aware of all the documents required for submission to the statutory authorities.

The architect will make available all the technical drawings and documents in the acceptable format with the required signatures and certificates to enable the client to submit applications and obtain approvals.

- Deliverables at stage IV

All documents and drawings are prescribed by the various statutory bodies.

Here is the flowchart that illustrates the steps and areas covered in each stage succinctly - (PDF)

Disclaimer

The architect shall bring to the notice of the client any of the services/ deliverables not under the scope before proceeding with the design. In the absence of any such disclosure, all services specified in these guidelines shall be deemed to be compensated fully in the fees of the architect.